## Per Activity Estimates
Activity | Average Duration (Days)
Requirements | 5
Architecture | 5
Project Planning | 5
Dev Training | 0
Solution Scaffolding, CM, CI, CD | 5
Test Plan | 5
Test Harness | 5
Activity-by-Activity Effort Estimations
Services/Components |  |  | Learning curves | Service Requirements Specification (SRS) | SRS Review | Service Test Plan (STP) | Some Construction/Prototyping throw away code | Detailed Design & Standardized Documentation | Design Review | Construction/ Implementation | Integration points with other components (bang to fit) | Test Client, Unit & Integration Tests | Code Review | Integration Testing | Installation/ Deployment | Documentation
UI Design | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Queue | 5 |  | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 2 | 0 | 1 | 0.5 | 0 | 0 | 0
SignalR Utility | 5 |  | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 2 | 0 | 1 | 0.5 | 0 | 0 | 0
Products Database | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.5 | 0 | 0.5 | 0
Product Accessor | 5 |  | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 2.5 | 0 | 1 | 0.5 | 0 | 0 | 0
Validation Engine | 5 |  | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 2.5 | 0 | 1 | 0.5 | 0 | 0 | 0
Product Manager | 5 |  | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 2.5 | 0 | 1 | 0.5 | 0 | 0 | 0
Notification Manager | 5 |  | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 2.5 | 0 | 1 | 0.5 | 0 | 0 | 0
API Client/Controllers | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 1 | 0.5 | 0 | 1 | 0
Web Client | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 1 | 0.5 | 0 | 1 | 0
System Testing | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
Total Days | 85

## Broadband Estimates
| Name | Duration | People | Outliers | Duration | People
1 | Dev1 | 0 | 0 | Low | 0 | 0
2 | Dev2 | 0 | 0 | High | 0 | 0
3 | Dev3 | 0 | 0
4 | Dev4 | 0 | 0
5 | Dev5 | 0 | 0
6 | Dev6 | 0 | 0
7 | QA1 | 0 | 0
8 | QA2 | 0 | 0
9 | QA3 | 0 | 0
10 | QA4 | 0 | 0
11 | PJM | 0 | 0
12 | PDM | 0 | 0
13 | BA1 | 0 | 0
14 | BA2 | 0 | 0
15 | DBA1 | 0 | 0
16 | DBA2 | 0 | 0
17 | TE1 | 0 | 0
18 | TE2 | 0 | 0
19 | DevLead | 0 | 0
20 | ARC1 | 0 | 0
| Average | 0 | 0
| SD | 0 | 0

## Dependencies
Id | Activity | Duration | Predecessors
1 | Requirements | 5
2 | Architecture | 5
3 | Project Planning | 5
4 | Solution Scaffolding, CM, CI, CD | 5
5 | Test Plan | 5
6 | Test Harness | 5
7 | UI Design | 5
8 | Queue | 5
9 | SignalR Utility | 5
10 | Products Database | 5
11 | Product Accessor | 5
12 | Validation Engine | 5
13 | Product Manager | 5
14 | Notification Manager | 5
15 | API Client | 5
16 | Web Client | 5
17 | System Testing | 5

## Shape of the Plan
ID | Owner | Activity | Duration | Planned Completion Date | Planned Earned Value
1 |  | Start | 0 | 2018-01-01 | 0%
2 |  | Requirements | 15 | 2018-01-19 | 3.529%
3 |  | Architecture | 20 | 2018-01-26 | 8.235%
4 |  | Project Planning | 20 | 2018-02-23 | 12.94%
5 |  | Dev Training | 5 | 2018-03-02 | 14.12%
6 |  | CM, CI, CD | 5 | 2018-03-02 | 15.29%
7 |  | Configuration | 5 | 2018-03-09 | 16.47%
8 |  | Queue | 5 | 2018-03-09 | 17.65%
9 |  | Database Tables, Views, Sprocs | 10 | 2018-03-16 | 20%
10 |  | Logging | 15 | 2018-03-23 | 23.53%
11 |  | Security | 20 | 2018-03-30 | 28.24%
12 |  | Infrastructure Done | 0 | 2018-03-30 | 28.24%
13 |  | Accessor4 | 5 | 2018-04-06 | 29.41%
14 |  | Test Plan | 30 | 2018-04-13 | 36.47%
15 |  | Accessor1 | 10 | 2018-04-13 | 38.82%
16 |  | Engine3 | 10 | 2018-04-13 | 41.18%
17 |  | Test Harness | 5 | 2018-04-20 | 42.35%
18 |  | UI Design | 15 | 2018-04-20 | 45.88%
19 |  | Accessor3 | 15 | 2018-04-20 | 49.41%
20 |  | Accessor2 | 20 | 2018-04-27 | 54.12%
21 |  | Engine1 | 20 | 2018-05-18 | 58.82%
22 |  | Engine2 | 25 | 2018-06-01 | 64.71%
23 |  | Manager1 | 15 | 2018-06-08 | 68.24%
24 |  | Manager2 | 20 | 2018-06-15 | 72.94%
25 |  | Manager3 | 25 | 2018-07-06 | 78.82%
26 |  | Customer Web Client | 25 | 2018-07-13 | 84.71%
27 |  | Administrative Web Client | 35 | 2018-08-24 | 92.94%
28 |  | System Testing | 30 | 2018-10-05 | 100%
|  | Total Planned Effort | 425

## Staffing
Date | Project Manager | Product Manager | Architect | Developers | Build/CM | Test Engineers | Testers | Total Cost (M/M) | Direct Cost | Indirect Cost
Start
2018-01-01 | 1 | 1 | 1 |  |  |  |  | 0 | 0 | 0
2018-01-19 | 1 | 1 | 1 |  |  |  |  | 1.8 | 0.6 | 1.2
2018-01-22 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.1 | 0.2
2018-02-16 | 1 | 1 | 1 |  |  |  |  | 2.5 | 0.83333 | 1.6667
2018-02-19 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.1 | 0.2
2018-03-16 | 1 | 1 | 1 |  |  |  |  | 2.5 | 0.83333 | 1.6667
2018-03-19 | 1 | 1 | 1 | 5 | 1 |  |  | 0.9 | 0.7 | 0.2
2018-03-23 | 1 | 1 | 1 | 5 | 1 |  |  | 1.2 | 0.93333 | 0.26667
2018-03-26 | 1 | 1 | 1 | 6 |  | 1 |  | 1 | 0.8 | 0.2
2018-03-30 | 1 | 1 | 1 | 6 |  | 1 |  | 1.3333 | 1.0667 | 0.26667
2018-04-06 | 1 | 1 | 1 | 6 |  | 1 |  | 2.3333 | 1.8667 | 0.46667
2018-04-13 | 1 | 1 | 1 | 5 |  | 1 |  | 2.1 | 1.6333 | 0.46667
2018-04-20 | 1 | 1 | 1 | 5 |  | 1 |  | 2.1 | 1.6333 | 0.46667
2018-04-23 | 1 | 1 | 1 | 6 |  | 1 |  | 1 | 0.8 | 0.2
2018-04-27 | 1 | 1 | 1 | 6 |  | 1 |  | 1.3333 | 1.0667 | 0.26667
2018-05-04 | 1 | 1 | 1 | 6 |  | 1 |  | 2.3333 | 1.8667 | 0.46667
2018-05-07 | 1 | 1 | 1 | 6 |  | 1 |  | 1 | 0.8 | 0.2
2018-05-11 | 1 | 1 | 1 | 6 |  | 1 |  | 1.3333 | 1.0667 | 0.26667
2018-05-14 | 1 | 1 | 1 | 3 |  |  |  | 0.6 | 0.4 | 0.2
2018-05-18 | 1 | 1 | 1 | 3 |  |  |  | 0.8 | 0.53333 | 0.26667
2018-05-21 | 1 | 1 | 1 | 3 |  |  |  | 0.6 | 0.4 | 0.2
2018-06-08 | 1 | 1 | 1 | 3 |  |  |  | 3.6 | 2.4 | 1.2
2018-06-11 | 1 | 1 | 1 | 3 |  |  |  | 0.6 | 0.4 | 0.2
2018-06-22 | 1 | 1 | 1 | 3 |  |  |  | 2.2 | 1.4667 | 0.73333
2018-06-25 | 1 | 1 | 1 | 3 |  |  |  | 0.6 | 0.4 | 0.2
2018-06-29 | 1 | 1 | 1 | 3 |  |  |  | 0.8 | 0.53333 | 0.26667
2018-07-02 | 1 | 1 | 1 | 3 |  |  |  | 0.6 | 0.4 | 0.2
2018-07-06 | 1 | 1 | 1 | 3 |  |  |  | 0.8 | 0.53333 | 0.26667
2018-07-27 | 1 | 1 | 1 | 2 |  |  |  | 3.5 | 2.1 | 1.4
2018-07-30 | 1 | 1 | 1 | 2 |  |  |  | 0.5 | 0.3 | 0.2
2018-08-03 | 1 | 1 | 1 | 2 |  |  |  | 0.66667 | 0.4 | 0.26667
2018-09-14 | 1 | 1 | 1 | 1 |  |  |  | 5.6 | 2.8 | 2.8
2018-09-17 | 1 | 1 | 1 |  |  | 1 | 1 | 0.5 | 0.3 | 0.2
2018-10-26 | 1 | 1 | 1 |  |  | 1 | 1 | 6.5 | 3.9 | 2.6
[7 empty] | Total | 53.8333 | 33.9667 | 19.8667

## Summary
| Overall | Construction Only
Cost in man months | 53.8333 | 46.4333
Duration in months | 9.2333 | 7.3667
Average staffing | 5.4195 | 6.3032
Effort in estimated MM | 14.1667 | 12.3333
9/1 efficiency factor | 26.32% | 26.56% | Ratio of Effort to Cost
Front End: | 19.13% | 24.42% | i.e. Requirements Analysis, System Design, Project Design

## Risk
Criticality Risk = 4*C + 3*R + 2*Y + 1*G / 4*N
Activity Risk = 1 - SUM(float)/number of activities * max(float)
[12 empty] | Phi = | 1.618
| ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.66667 | Activity Risk | 0.80247 | Fibonacci Formula | 0.62757
| 1 | Requirements | 0 | 1 | 0 | 0 | 0 |  |  | Fibonacci Formula | 0.6822
| 2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Planning | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Dev Training | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
| 5 | CM, CI, CD | 0 | 1 | 0 | 0 | 0 | Green Factor | 1
| 6 | Test Plan | 90 | 0 | 0 | 0 | 1
| 7 | Test Harness | 90 | 0 | 0 | 0 | 1 | Total | 10
| 8 | UI Design | 55 | 0 | 0 | 0 | 1
| 9 | Security | 0 | 1 | 0 | 0 | 0
| 10 | Configuration | 15 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Logging | 5 | 0 | 1 | 0 | 0 | Yellow Limit | 26
| 12 | Queue | 15 | 0 | 0 | 1 | 0
| 13 | Infrastructure Done | 0 | 1 | 0 | 0 | 0
| 14 | Database Tables, Views, Sprocs | 10 | 0 | 0 | 1 | 0
| 15 | Accessor1 | 35 | 0 | 0 | 0 | 1
| 16 | Accessor2 | 0 | 1 | 0 | 0 | 0
| 17 | Accessor3 | 10 | 0 | 0 | 1 | 0
| 18 | Accessor4 | 45 | 0 | 0 | 0 | 1
| 19 | Engine1 | 10 | 0 | 0 | 1 | 0
| 20 | Engine2 | 0 | 1 | 0 | 0 | 0
| 21 | Engine3 | 35 | 0 | 0 | 0 | 1
| 22 | Manager1 | 20 | 0 | 0 | 1 | 0
| 23 | Manager2 | 15 | 0 | 0 | 1 | 0
| 24 | Manager3 | 0 | 1 | 0 | 0 | 0
| 25 | Customer Web Client | 30 | 0 | 0 | 0 | 1
| 26 | Administrative Web Client | 0 | 1 | 0 | 0 | 0
| 27 | System Testing | 0 | 1 | 0 | 0 | 0
|  | Total | 480 | 12 | 1 | 7 | 7